## Risks analysis
Assignment: define risks and mitigation measures for 10 year functionality of WASH services
Project:
Partner:
| Phase | Description | Chance it will occur | Impact if it occurs | Mitigation Measure
|  |  | High | High | 1 What should be done to avoid or mitigate the risk? (can be more than one measure)
|  |  | Medium | Medium | 2 By whom? (can be more than one partner, eg: community, government body, private sector party, ngo, (..)
|  |  | Low | Low | 3 What agreement will be made between you (ngo) and the other parties to ensure 10 year functionality of the facility?
Financial | At project start | people they don’t have enough money to contribute when we implement the project |  |  | sensitize community to contribute in kind.
| During implementation | fail to fullfill to condition of accessing and using of construction material. Also missuse of funds from community water suplly projects |  |  | sensitize community on condition of accessing and use of construction material and installation of water vending machine and application of mobile banking system.
| After handing over | financial suistanability exit strategy not prepared and executed. |  |  | financial suistanability plan should be prepared and executed.
Institutional | At project start | absence of WASH sector operational committee at village level. |  |  | select and establish operational committee based on project goal and objectives
| During implementation | inactive WASH sector operational committee at village level |  |  | select and establish operational committee based on project goal and objectives
| After handing over | committee operations not intergrated into village development committee plans. |  |  | integration of committee operations into vilage development plans and ensure by laws supporting its operation are properly reinforced
Environmental | At project start | environmental issues were not clear embeded into project implementation strategies. |  |  | during project design … will take into consideration environmental issues into its project implimentation strategies.
| During implementation | undertaking water quality test and observation of soil texture |  |  | ... in corrabolation with regional water laboratory will perfome water quality test to ensure water from the borehole fit into human consumption.
| After handing over | environmental issues not included into village developmemt development plan. |  |  | ... train village government member on preparation of village development plan with emphasis on interacting of environmental issues on village plan.
Technical | At project start | improper project design of water supply and sanitation facilities infrastructure |  |  | ... to redesign project infrastucture after conducting geological and topographical survey.
| During implementation | low knowledge of using innovative infrastructure like water vending machine. |  |  | community sensitization on proper use of innovative infrastructure installed.
| After handing over | depature of trained pump and engine attendants and local artisan to other village or engage to the other activities. |  |  | establishment of local contract between ..., village government and pump and engine attendant on project monitoring and evaluation.
Social | At project start | low community participation in project design |  |  | sensitization meeting to facilitate community to full participate on project design.
| During implementation | community fail to fulfill their responsibilities |  |  | ... in corrabolation with village government and District executive officer establish memorandum of understanding on project implementation which will describe rules and responsibilities of each parts involved in project implementation .
| After handing over | low security of project infrastructure |  |  | reinforcement of memorandum of understanding implementation which desribe rule and responsibilities of each parties on project suistanability.
Force Majeur | 'Force Majeur':
Unforeseen events,
Natural disasters which
can not be prevented
Or other
EXAMPLES and SUGGESTIONS